## Master
User Story: As a person who enjoys listening to music while walking, I want the Spotify playlist generator app to create a playlist that's tailored to my location and the current weather conditions. If I'm in the park on a sunny day, I want the app to create a playlist with upbeat, energetic music that matches the weather of where I am.
Task | Estimated Hours
Research and select weather and location APIs | 2
Develop location-based playlist algorithm | 3
Develop weather-based playlist algorithm | 3
Combine location and weather algorithms to generate playlist | 2
Integrate Spotify API for retrieving playlists and adding new playlist | 2
Develop algorithm to filter and rank playlists based on user's listening history and preferences | 4
Implement user authentication and authorization | 2
Design and develop user interface for the app | 6
Test and refine the playlist generation algorithm | 3
Total | 25

## Elaine
User Story: As a person who enjoys listening to music while walking, I want the Spotify playlist generator app to create a playlist that's tailored to my location and the current weather conditions. If I'm in the park on a sunny day, I want the app to create a playlist with upbeat, energetic music that matches the weather of where I am.
Task | Estimated Hours
Research and select weather and location APIs | 2
Set up API authentication and authorization | 2
Develop location-based playlist algorithm | 3
Develop weather-based playlist algorithm | 3
Combine location and weather algorithms to generate playlist | 2
Implement user authentication and authorization | 2
Develop user profile preferences | 2
Incorporate user profile preferences into playlist algorithm | 2
Test and refine the playlist generation algorithm | 2
Total: | 20

## Truda
User Story: As a person who enjoys listening to music while walking, I want the Spotify playlist generator app to create a playlist that's tailored to my location and the current weather conditions. If I'm in the park on a sunny day, I want the app to create a playlist with upbeat, energetic music that matches the weather of where I am.
Task | Estimated Hours
Research and select weather and location APIs | 3
Set up API authentication and authorization | 3
Design and develop user interface for the app | 6
Develop algorithm to map weather conditions to music genres/moods | 4
Integrate Spotify API for retrieving playlists and adding new playlist | 4
Develop algorithm to filter and rank playlists based on user's listening history and preferences | 6
Test and refine the playlist generation algorithm | 4
Total | 30

## Jackson
User Story: As a person who enjoys listening to music while walking, I want the Spotify playlist generator app to create a playlist that's tailored to my location and the current weather conditions. If I'm in the park on a sunny day, I want the app to create a playlist with upbeat, energetic music that matches the weather of where I am.
Task | Estimated Hours
Research and select weather and location APIs | 2
Set up API authentication and authorization | 2
Develop location-based playlist algorithm | 4
Develop weather-based playlist algorithm | 4
Combine location and weather algorithms to generate playlist | 4
Implement user authentication and authorization | 2
Develop user feedback system for playlist suggestions | 4
Incorporate user feedback into playlist generation algorithm | 4
Test and refine the playlist generation algorithm | 4
Total: | 28